## Output_Operations
Operation ID | Vessel ID | Type | Product | Source | Target | Volume (t) | Start Time | Duration (h) | End Time | Line | Wagons | Locked | Notes
RAIL_1 |  | rail_batch | sunflower | Rail | RVS-1 | 1170 | 2025-01-10 | 6 | 2025-01-10 06:00 |  | 18 | No
RAIL_2 |  | rail_batch | sunflower | Rail | RVS-1 | 2340 | 2025-01-11 | 12 | 2025-01-11 12:00 |  | 36 | No
RAIL_3 |  | rail_batch | sunflower | Rail | RVS-1 | 3510 | 2025-01-12 | 18 | 2025-01-12 18:00 |  | 54 | No
RAIL_4 |  | rail_batch | sunflower | Rail | RVS-1 | 1170 | 2025-01-13 | 6 | 2025-01-13 06:00 |  | 18 | No
RAIL_5 |  | rail_batch | sunflower | Rail | RVS-1 | 2340 | 2025-01-14 | 12 | 2025-01-14 12:00 |  | 36 | No
BERTH_0001 | MV-PALMOIL1 | berthing |  |  | BERTH_PALM | 0 | 2025-01-18 14:00 | 1.5 | 2025-01-18 15:30 |  |  | No | Berthing MV-PALMOIL1 at BERTH_PALM
DISCH_0002 | MV-PALMOIL1 | discharge | Olein | Ship_MV-PALMOIL1_H2 | RVS_3 | 8000 | 2025-01-18 17:30 | 8.8889 | 2025-01-19 02:23 | Line1 |  | No | Discharge H2: Olein
DISCH_0003 | MV-PALMOIL1 | discharge | Stearin | Ship_MV-PALMOIL1_H1 | SHT | 5000 | 2025-01-18 17:30 | 10 | 2025-01-19 03:30 | Line2 |  | No | Discharge H1: Stearin to SHT
XFER_0004 |  | transfer | Stearin | SHT | Rail | 5000 | 2025-01-19 05:30 | 10 | 2025-01-19 15:30 |  | 77 | No | Transfer Stearin from SHT to rail
CLEAN_L2_0005 | MV-PALMOIL1 | cleaning |  |  | Line2 | 0 | 2025-01-19 17:30 | 4 | 2025-01-19 21:30 |  |  | No | Cleaning Line2 from Stearin to LOW3MCPD
CLEAN_0006 | MV-PALMOIL1 | cleaning |  |  | SHT | 0 | 2025-01-19 22:00 | 72 | 2025-01-22 22:00 |  |  | No | Cleaning SHT from Stearin to LOW3MCPD
DISCH_0007 | MV-PALMOIL1 | discharge | LOW3MCPD | Ship_MV-PALMOIL1_H3 | SHT | 5000 | 2025-01-23 | 10 | 2025-01-23 10:00 | Line2 |  | No | Discharge H3: LOW3MCPD to SHT
XFER_0008 |  | transfer | LOW3MCPD | SHT | Rail | 5000 | 2025-01-23 12:00 | 10 | 2025-01-23 22:00 |  | 77 | No | Transfer LOW3MCPD from SHT to rail
UNBERTH_0009 | MV-PALMOIL1 | unberthing |  |  | BERTH_PALM | 0 | 2025-01-24 | 4 | 2025-01-24 04:00 |  |  | No | Unberthing MV-PALMOIL1 from BERTH_PALM

## Output_Balances
| hour | time | RVS_1_flow_in | RVS_2_flow_in | RVS_3_flow_in | RVS_5_flow_in | SHT_flow_in | RVS_1_flow_out | RVS_2_flow_out | RVS_3_flow_out | RVS_5_flow_out | SHT_flow_out | RVS_1_volume | RVS_2_volume | RVS_3_volume | RVS_5_volume | SHT_volume
0 | 0 | 2026-01-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 2025-01-10 01:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | 2025-01-10 02:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | 2025-01-10 03:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 4 | 2025-01-10 04:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 5 | 2025-01-10 05:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 6 | 2025-01-10 06:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 7 | 2025-01-10 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 8 | 2025-01-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 9 | 2025-01-10 09:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Output_Wagons_Summary
total_wagons_needed | peak_demand | gap_count | estimated_cost
316 | 77 | 0 | 0

## Output_Wagons_Daily
Date | Total Wagons | Operations
2025-01-10 | 18 | RAIL_1
2025-01-11 | 36 | RAIL_2
2025-01-12 | 54 | RAIL_3
2025-01-13 | 18 | RAIL_4
2025-01-14 | 36 | RAIL_5
2025-01-19 | 77 | XFER_0004
2025-01-23 | 77 | XFER_0008

## Output_Risks_Critical
op_id | reason | slack_hours | severity
UNBERTH_0009 | Operation UNBERTH_0009 is on critical path with zero slack. Any delay will delay project completion. | 0 | high

## Output_Risks_Recs
priority | item | reason | action
HIGH | Monitor UNBERTH_0009 closely | Operation UNBERTH_0009 is on critical path with zero slack. Any delay will delay project completion. | Ensure no delays in dependent operations
HIGH | Operation UNBERTH_0009 is on critical path with zero slack. Any delay will delay project completion. | 150000 | Add contingency time or allocate additional resources

## Gantt_Chart
Resource | 10-00 | 10-06 | 10-12 | 10-18 | 11-00 | 11-06 | 11-12 | 11-18 | 12-00 | 12-06 | 12-12 | 12-18 | 13-00 | 13-06 | 13-12 | 13-18 | 14-00 | 14-06 | 14-12 | 14-18 | 15-00 | 15-06 | 15-12 | 15-18 | 16-00 | 16-06 | 16-12 | 16-18 | 17-00 | 17-06 | 17-12 | 17-18 | 18-00 | 18-06 | 18-12 | 18-18 | 19-00 | 19-06 | 19-12 | 19-18 | 20-00 | 20-06 | 20-12 | 20-18 | 21-00 | 21-06 | 21-12 | 21-18 | 22-00 | 22-06 | 22-12 | 22-18 | 23-00 | 23-06 | 23-12 | 23-18 | 24-00 | 24-06 | 24-12 | 24-18 | 25-00 | 25-06 | 25-12 | 25-18 | 26-00 | 26-06 | 26-12 | 26-18 | 27-00 | 27-06 | 27-12 | 27-18 | 28-00 | 28-06 | 28-12 | 28-18 | 29-00 | 29-06 | 29-12 | 29-18 | 30-00 | 30-06 | 30-12 | 30-18 | 31-00 | 31-06 | 31-12 | 31-18 | 01-00 | 01-06 | 01-12 | 01-18 | 02-00 | 02-06 | 02-12 | 02-18 | 03-00 | 03-06 | 03-12 | 03-18 | 04-00 | 04-06 | 04-12 | 04-18 | 05-00 | 05-06 | 05-12 | 05-18 | 06-00 | 06-06 | 06-12 | 06-18 | 07-00 | 07-06 | 07-12 | 07-18 | 08-00 | 08-06 | 08-12 | 08-18 | 09-00
BERTH | [34 empty] | DISCH_0003 | [17 empty] | DISCH_0007 |  |  |  | UNBERTH_0009
Line1 | [34 empty] | DISCH_0002
Line2 | [34 empty] | DISCH_0003 |  |  |  | CLEAN_L2_0005 | [13 empty] | DISCH_0007
RVS-1 | RAIL_1 |  |  |  | RAIL_2 |  |  |  | RAIL_3 |  |  |  | RAIL_4 |  |  |  | RAIL_5
RVS-2
RVS-3
RVS-5
SHT | [34 empty] | DISCH_0003 |  | XFER_0004 |  |  | CLEAN_0006 | [12 empty] | DISCH_0007 |  | XFER_0008
Rail | RAIL_1 |  |  |  | RAIL_2 |  |  |  | RAIL_3 |  |  |  | RAIL_4 |  |  |  | RAIL_5 | [19 empty] | XFER_0004 | [17 empty] | XFER_0008